## Tracker
Update on: 21st April 2026 |  | Reliance FFDC Project - Phase 2
Sr No | Head | FFDC SPOC | Hone ST SPOC | RAW Link | RAW Content Received | SB Submission Date | SB Link | SB Feedback/Update from FFDC Team | Revised SB Submission by Hone ST Team | SB Approval from FFDC Team | Alpha Submission by Hone ST Team | Alpha Feedback/Update by FFDC Team | Final Alpha Submission by Hone ST Team | Alpha Approval (with feedbacks/updates) by FFDC Team | Gold Submission by Hone ST Team | Gold Feedback/Update by FFDC Team | Final Gold Submission by Hone ST Team | Gold Approval by FFDC Team | SCORM Delivery by Hone ST Team | Remarks (Current Status and Challenges)
1 | M29_FFDC Consumable Management | Reepal | Akash | Consumable Management Process.pptx | 2026-04-13 | 2026-04-20 | Consumable Management Process
2 | M30_ Vendor Query Management | Reepal | Akash | Vendor Query Management (1).pptx | 2026-04-13 | 2026-04-17 | Vendor Query Management | Awaiting Feedback
3 | M31_Capex Demand Process | Ajay | Ritesh
4 | M32_Scrap Management Process | Gopal | Mayank
5 | M33_Trip Creation Process | Anuradha | Anusha | Trip Creation Process Final updated version.pptx | 2026-04-17 | 2026-04-24 | Trip Creation Process
6 | M34_Trip Start & Intimation Sending | Anuradha | Anusha | Trip Start Intimation Process.pptx | 2026-04-20 | 2026-04-25 | Trip Start Intimation Process
7 | M35_FFDC Dashboard | Srinivas | Akash
8 | M36_Service Entry to Vendor Payment - SSO | Reepal | Mayank
9 | M37_NRR Management Process | Gopal | Anusha
10 | M38_Dumping Process | Srinivas | Ritesh
11 | M39_AQR Process | Nityanand | Akash
12 | M40_Picklist Creation Process | Nityanand | Mayank
13 | M41_GRN Process | Joy | Juned | FFDC_Receiving-GRN.pptx | 2026-04-20 | 2026-04-25 | FFDC GRN Process
14 | M42_Crating & Barcoding Process | Joy | Shubhangi | Crating_and_Barcoding_Process_Latest.pptx | 2026-04-20 | 2026-04-25 | Crating and Barcoding
15 | M43_Floor Walk & Check Sheets | Gopal | Akash
16 | M44_PI Process for Non F&V | Bisworanjan | Mayank
17 | M45_Trip Closing Process | Anuradha | Juned | Trip Closing DMS Process 16 Apr.pptx | 2026-04-18 | 2026-04-22 | Trip Closing & DMS Process
18 | M46_T-POD & M-POD | Rahul | Ritesh
19 | M47_DMS Process | Joy | Akash
20 | M48_Cold Chain Process | Gopal | Mayank

## Timelines
Sr No | Head | FFDC SPOC | Hone ST SPOC | RAW Content Received | SB Submission | SB Feedback/Update | Revised SB Submission | SB Approval | Alpha Submission | Alpha Feedback/Update | Final Alpha Submission | Alpha Approval (with feedbacks/updates) | Gold Submission | Gold Feedback/Update | Final Gold Submission | Gold Approval | SCORM Delivery (No. Of Days Required)
1 | FFDC Consumable Management | Reepal | Anusha | 2026-04-13 | 2026-04-20 | 2026-04-21 | 2026-04-24 | 2026-04-25 | 2026-05-02 | 2026-05-04 | 2026-05-09 | 2026-05-11 | 2026-05-16 | 2026-05-18 | 2026-05-22 | 2026-05-23 | 2026-05-30
2 | Vendor Query Management | Reepal | Akash | 2026-04-13 | 2026-04-20 | 2026-04-21 | 2026-04-24 | 2026-04-25 | 2026-05-02 | 2026-05-04 | 2026-05-09 | 2026-05-11 | 2026-05-16 | 2026-05-18 | 2026-05-22 | 2026-05-23 | 2026-05-30
3 | Capex Demand Process | Ajay | Ritesh | 2026-04-13 | 2026-04-20 | 2026-04-21 | 2026-04-24 | 2026-04-25 | 2026-05-02 | 2026-05-04 | 2026-05-09 | 2026-05-11 | 2026-05-16 | 2026-05-18 | 2026-05-22 | 2026-05-23 | 2026-05-30
4 | Scrap Management Process | Gopal | Mayank | 2026-04-13 | 2026-04-20 | 2026-04-21 | 2026-04-24 | 2026-04-25 | 2026-05-02 | 2026-05-04 | 2026-05-09 | 2026-05-11 | 2026-05-16 | 2026-05-18 | 2026-05-22 | 2026-05-23 | 2026-05-30
5 | Trip Creation Process | Anuradha | Anusha | 2026-04-17 | 2026-04-24 | 2026-04-25 | 2026-04-29 | 2026-04-30 | 2026-05-07 | 2026-05-08 | 2026-05-12 | 2026-05-13 | 2026-05-20 | 2026-05-21 | 2026-05-25 | 2026-05-26 | 2026-06-01
6 | Trip Start & Intimation Sending | Anuradha | Ritesh | 2026-04-17 | 2026-04-24 | 2026-04-25 | 2026-04-29 | 2026-04-30 | 2026-05-07 | 2026-05-08 | 2026-05-12 | 2026-05-13 | 2026-05-20 | 2026-05-21 | 2026-05-25 | 2026-05-26 | 2026-06-01
7 | FFDC Dashboard | Srinivas | Akash | 2026-04-17 | 2026-04-24 | 2026-04-25 | 2026-04-29 | 2026-04-30 | 2026-05-07 | 2026-05-08 | 2026-05-12 | 2026-05-13 | 2026-05-20 | 2026-05-21 | 2026-05-25 | 2026-05-26 | 2026-06-01
8 | Service Entry to Vendor Payment - SSO | Reepal | Mayank | 2026-04-17 | 2026-04-24 | 2026-04-25 | 2026-04-29 | 2026-04-30 | 2026-05-07 | 2026-05-08 | 2026-05-12 | 2026-05-13 | 2026-05-20 | 2026-05-21 | 2026-05-25 | 2026-05-26 | 2026-06-01
9 | NRR Management Process | Gopal | Anusha | 2026-04-22 | 2026-04-29 | 2026-04-30 | 2026-05-04 | 2026-05-05 | 2026-05-12 | 2026-05-13 | 2026-05-16 | 2026-05-18 | 2026-05-22 | 2026-05-23 | 2026-05-27 | 2026-05-28 | 2026-06-04
10 | Dumping Process | Srinivas | Ritesh | 2026-04-22 | 2026-04-29 | 2026-04-30 | 2026-05-04 | 2026-05-05 | 2026-05-12 | 2026-05-13 | 2026-05-16 | 2026-05-18 | 2026-05-22 | 2026-05-23 | 2026-05-27 | 2026-05-28 | 2026-06-04
11 | AQR Process | Nityanand | Akash | 2026-04-22 | 2026-04-29 | 2026-04-30 | 2026-05-04 | 2026-05-05 | 2026-05-12 | 2026-05-13 | 2026-05-16 | 2026-05-18 | 2026-05-22 | 2026-05-23 | 2026-05-27 | 2026-05-28 | 2026-06-04
12 | Picklist Creation Process | Nityanand | Mayank | 2026-04-22 | 2026-04-29 | 2026-04-30 | 2026-05-04 | 2026-05-05 | 2026-05-12 | 2026-05-13 | 2026-05-16 | 2026-05-18 | 2026-05-22 | 2026-05-23 | 2026-05-27 | 2026-05-28 | 2026-06-04
13 | GRN Process | Joy | Anusha | 2026-04-27 | 2026-05-02 | 2026-05-04 | 2026-05-08 | 2026-05-09 | 2026-05-16 | 2026-05-17 | 2026-05-21 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-05-30 | 2026-06-01 | 2026-06-06
14 | Carrating & Barcoding Process | Joy | Ritesh | 2026-04-27 | 2026-05-02 | 2026-05-04 | 2026-05-08 | 2026-05-09 | 2026-05-16 | 2026-05-17 | 2026-05-21 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-05-30 | 2026-06-01 | 2026-06-06
15 | Floor Walk & Check Sheets | Gopal | Akash | 2026-04-27 | 2026-05-02 | 2026-05-04 | 2026-05-08 | 2026-05-09 | 2026-05-16 | 2026-05-17 | 2026-05-21 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-05-30 | 2026-06-01 | 2026-06-06
16 | PI Process for Non F&V | Bisworanjan | Mayank | 2026-04-27 | 2026-05-02 | 2026-05-04 | 2026-05-08 | 2026-05-09 | 2026-05-16 | 2026-05-17 | 2026-05-21 | 2026-05-22 | 2026-05-25 | 2026-05-26 | 2026-05-30 | 2026-06-01 | 2026-06-06
17 | Trip Closing Process | Anuradha | Anusha | 2026-05-02 | 2026-05-09 | 2026-05-11 | 2026-05-15 | 2026-05-16 | 2026-05-23 | 2026-05-25 | 2026-05-30 | 2026-06-01 | 2026-06-04 | 2026-06-05 | 2026-06-09 | 2026-06-10 | 2026-06-16
18 | T-POD & M-POD | Rahul | Ritesh | 2026-05-02 | 2026-05-09 | 2026-05-11 | 2026-05-15 | 2026-05-16 | 2026-05-23 | 2026-05-25 | 2026-05-30 | 2026-06-01 | 2026-06-04 | 2026-06-05 | 2026-06-09 | 2026-06-10 | 2026-06-16
19 | DMS Process | Joy | Akash | 2026-05-02 | 2026-05-09 | 2026-05-11 | 2026-05-15 | 2026-05-16 | 2026-05-23 | 2026-05-25 | 2026-05-30 | 2026-06-01 | 2026-06-04 | 2026-06-05 | 2026-06-09 | 2026-06-10 | 2026-06-16
20 | Cold Chain Process | Gopal | Mayank | 2026-05-02 | 2026-05-09 | 2026-05-11 | 2026-05-15 | 2026-05-16 | 2026-05-23 | 2026-05-25 | 2026-05-30 | 2026-06-01 | 2026-06-04 | 2026-06-05 | 2026-06-09 | 2026-06-10 | 2026-06-16
Note:
At any given point in time Hone ST Team will be working on 4 modules